## 1 GIA
Gender impact assessments
Table 1 - Gender impact assessments progress
Required | Required | Required | Required | Required | Required | Recommended | Recommended
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Safer Communities Strategy and Policy | Policy | Provide strategic direction for Council’s community safety and crime prevention work that aligns with the Community Vision, Council Plan and other key Council strategies. A new long term document (10 years), that will provide an authorising environment and set the strategic direction to create a common understanding across Council, with a primary prevention focus to improve community safety in Frankston City. The Strategy will provide the strategic framework to guide decision making and the policy will provide the authorising environment for Council departments to develop and implement initiatives that promote and enhance safety in the community. | New | Yes | Focus on collective action, on the attributes identified as experiencing disproportionate levels of safety, which are: gender inequality, racism and discrimination. To improve community safety through building community cohesion, inclusion, tolerance and acceptance. To inform the review and development of Council’s action plans and collect evaluation measures that can show collectively the impact of our actions to improve community safety. To address the multiple facets of community safety, the needs and circumstances of different segments of the community will be considered by applying an intersectional lens to the development of action plans that contribute to strategy implementation. To have actions that aim to identify and remove structural barriers to participation and inclusion such as gender, culture, age, ability, sexual orientation, religion. Improve organisational capability to capture, monitor and evaluate progress towards intersectional gender equality. Key actions • Action plans will undertake broad and inclusive consultation including priority population groups to gain an understanding of their unique needs and lived experiences. • Consultation and research data will be disaggregated and analysed through an intersectional lens. • A minimum of one action should be focused on removing barriers to inclusion in priority population groups e.g. non gendered / human inclusive language, messaging, symbols and signage, celebrating and recognising different cultural identities. • A minimum of one action should be designed that does not reinforce gender stereotypes (e.g. challenge community attitudes; education training, awareness raising campaigns). • To achieve collective impact; data should be collated and made accessible within the organisation to monitor change over time. This will also enable Council to demonstrate how we are collectively progressing gender equality and community safety. • Shared progress measures will be used to capture data from across the organisation to measure collective impact. | Yes | When understanding disproportionate levels of safety in the community an intersectional lens was applied, and through this gender inequality, racism and discrimination were identified as priority areas for collective action. Key actions included: - gathering and use of disaggregated data to assist with intersectional analysis - actions focused on removing barriers to inclusion for various and intersecting attributes
Glass recycling bin implementation plan | Service | Implementing a glass recycling bin to all residents in the Frankston City LGA | New | Yes | An education and engagement officer position was introduced, to be in the field during the preparation and delivery phases of the initiative to support with delivering targeted education and communications and available to respond to unidentified community needs. An education and communication strategy that challenges outdated gender stereotypes with targeted strategies to reach and educate men to enable a shared approach to waste management in the home. | Yes | Communications strategy with targeted strategies to reach and educate community leaders who support culturally and linguitically diverse communities and promotion of our 'wheel in, wheel out' service for people experiencing or living with a disability.
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review | Yes | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. | Yes | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.

## 2.1 Strategies and measures
Strategies and measures
Table 2.1 - Strategies and measures progress
Required | Required | Required | Recommended | Recommended | Recommended | Recommended
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Indicators key
List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. | [6 empty] | 1. 2. 3. 4. 5. 6. 7. | Gender composition of all levels of the workforce. Gender composition of governing bodies. Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender. Sexual harassment in the workplace Recruitment and promotion practices in the workplace. Availability and utilisation of terms, conditions and pratices relating to: - family violence leave - flexible working arrangements - working arrangements supporting employees with family or caring responsibilities Gendered segregation within the workplace
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7
Apply an intersectional gender lens to recruitment practices for leaders (contracts with agencies) | In progress | In early 2023, we mapped our recruitment processes, identifing enhancements that could be made and relevant documents that required updates. A review of our Code of Conduct, Capability Based Interview Question Guide, Selection Report Template, Selection Notes Template, Reference Check Template, Recruitment and Selection Guidelines, and Induction Checklist were completed. Due to personnel changes in our People Services team, the final review and endorsement was placed on-hold. In the interim, a consultation was held with our Diversity and Inclusion Group regarding recruitment practices. The findings will inform further enhancements to our recruitment practices. | Although this action was anticipated to be completed, we have made considerable progress and this delay will ensure our new EBA and payroll system are included in any further policy changes. | 2022 - 2023 | People and Services and Gender Equality Advisor | x
Review leaders' job descriptions | Complete | A of review was conducted in March-April 2023. | Identified a need to increase visibility of leader's role to progress gender equality and establish accountability. | 2023 - 2025 | People and Services and Gender Equality Advisor (GEA) | x
Apply a gender lens to Kickstart leaders program (track by gender) | Complete | In early 2022 a gender lens was applied to the Kickstart leaders program, which resulted in a gender ratio of participants representative of our organisation. | Participants in the most recent Kickstart program, consisted of 11 (69%) women and 5 (31%) men, reflective of Council's gendered workforce. | 2022 | Learning and Development | x
Exiting leaders interview with external provider | In progress | In August 2022 Council introduced an exit survey to all staff. The exit survey is administered by an external provider. Council have identified an external provider to deliver exit interviews to leaders. To finalise this action Council will update the exit process to include an interview option. | 61 exit survey responses were received and majority of respondents were women and no exiting staff requested an interview. The majority of respondents reported the reason they left Council was due to career advancement followed by workplace manager/s. Respondents reported what makes Council a truly great place to work is good support followed by teamwork and enjoyment and the reason provided for why Council is not a great place to work is culture, followed by workplace manager/s. | 2024 - 2025 | People & Culture | x
Inclusive leadership/gender equity training delivered to all leaders | Ongoing | In assessing organisational capability an Inclusive GE Leadership training program was designed to build a strong foundation within our leadership group. A three-part webinar series was delivered followed by small group coaching sessions facilitated by Women's Health in the South East (WHISE). In response to leaders feedback and assessing levels of knowledge and confidence this training action has become an ongoing GEAP action. Council wants to continue to build and enhance leader's capability to progress GE. Additional training has been booked for 2023-24. All people leaders, inclusive of Executives, Managers, Coordinators and Team Leaders were invited to participate in the training. The online webinars were delivered three times each, with all webinars delivered between November 2022 and March 2023. A recorded version of each webinar was uploaded to our online learning portal for new leaders and leaders who were unable to complete webinars. Small group coaching sessions were delivered post the webinars, April to June 2023. Coaching sessions provided leaders with a safe space to ask questions, build upon their understanding of gender equality and discuss their role in creating transformational change at Council. Leaders were guided to identify actions they could take to progress GE within their sphere of influence. | Participation 88% of leaders completed webinar 1, 63% completed webinar 2, 57% completed webinar 3 and 40% participated in the small group coaching sessions. Of our senior management group (EMT and Mangers), 88% completed 25% of the program, 27% completed 75% of the training and 22% completed 100% of the training program. Value WHISE calculated the Social Impact value of the training program delivered. The net benefits of the program are $907,618. This represents a benefit cost ratio of 127.92. The net benefit per participant was $7,147. The evaluation demonstrated changes in participant's knowledge and confidence. Anecdotal evidence received from leaders post their coaching session demonstrated these were powerful and effective in building understanding and demonstrating organisational commitment to progressing GE. Findings from the coaching sessions demonstrated the value of reflective pracitce and creating spaces for leaders to consolidate their learnings and work collaboartively. | 2022 | Culture & Capability and GEA | x
Leaders onboarding inclusive of Inclusive Leadership training | In progress | Online Inclusive GE training webinars are available for new people leaders to complete via Council's online training platform. The webinars will be developed into an interactive learning module in 2023-24. | The recorded webinars were effective in providing key information to leaders who missed the live webinars and provided a reference point for leaders to refer back to. The online webinars deliver important content but the duration is too long and not engaging for the end user. An interactive learning module is required to provide this education to leaders. | 2023 - 2025 | Culture & Capability and GEA | x
Update leaders job descriptions to include gender equitable and inclusive leadership | Complete | A result of the review conducted in March-April 2023 identified challenges with updating all leaders' job descriptions. The process of changing job descriptions is not straightforward and resource intensive. The desired outcome of this action is increased accountability and an ability to measure progress. Through the review process a systematic solution was found. Inclusion of a gender equality (GE) goal with 7 measures was embedded into the performance plan template for managers. The change will come into effect as part of developing 2023-24 plans. | Whilst the output of this action changed, the outcome will increase visibility of this work requirement, encourage action and improve accountability and monitoring of progress. Staff are encouraged at points throughout the performance plan period to review and update their plan. Including a GE goal in manager work plans provides a reminder of their requirement to progress GE and holds leaders accountable for implementing changes that progress GE. | 2023 | People Services, Learning and Development and GEA | x
Leaders' KPIs updated to include at least one regarding gender equitable and inclusive leadership | Complete | Through the job description review, mentioned above, it was identified that one KPI would not adequately progress GE. A gender equality goal was developed with 7 KPIs. The KPIs include: completing GE training; understanding pay disparity within their team and rectifying; creating opportunities for part-time worker to access higher duties and secondments; promote staff benefits and supports to staff including flexible work arrangements, paid and unpaid leave to men and family violence leave; promote the reporting of bullying, harassment and discrimination and sexual harassment; use inclusive language in all communications; ensure gender impact assessments are completed for all relevant initiatives. | All managers from 2023-24 will have a gender equality goal in their work plan and be accountable for progressing GE. | 2023 - 2025 | Learning and Development and GEA | x
Whole of organisation Gender Equity and Bystander training rolled out departmentally | In progress | Between January and May 2023, in-person 'Introduction to Gender Equality' sessions were delivered across Council. Nine teams participated including Sustainable Assets, Governance, City Futures Department, People & Culture, Engineering Services, Home Maintenance, Maternal and Child Health, Family Health and Arts and Culture. Training is scheduled for September with Council's Operations department. Council allocated funding to develop an online training package for staff in 2023-24. The online training package will include a bystander intervention module. | In-person presentations were informative and gained understanding of staff knowledge and organisational readiness for change. Funding secured to develop a sustainable online training program to build a foundation of understanding, knowledge and skills within Council's workforce. Outcomes: A sexual harassment report was received post a 'introduction to GE' session being delivered and a request for a session on sexual harassment was received and delivered to one team who requested additional education. Council received multiple complaints from staff after attending training where an external provider used an example that was discriminatory and reinforced outdated gender norms. Following this, Council informed the training provider and a commitment was made by the provider that they would deliver education to their trainers and staff. | 2022 - 2023 | Culture & Capability and GEA | x
Communicate the needs for intersectional data collection to Council and address privacy issues | In progress | Initial meetings identified that personal identity data of Councillors is not collected by Council. A privacy statement was developed and approach to inform and gather this information from Councillors was implemented. A communication was sent to the Mayor and Councillor Office to communicate and encourage Councillor participation. Advocacy to MAV has occurred requesting a sector-wide approach to gaining Councillor data and MAV have responded that they will explore options with LGV and/or VEC. | A privacy statement was developed and approach to inform and gather this information from Councillors was implemented. Further education is required to enhance Councillor understanding and gain Councillor engagement. | 2022 | Governance and GEA |  | x
Provide all Councillors with the opportunity to update details regarding their attributes | In progress | Councillors were provided with information on the value of collecting data about their identity and invited to provide their personal attribute information. Due to the nature and public visibility of the information Councillor's were given the option to disclose none, some or all information. | Three (33%) Councillors provided a full data response. | 2022 | Governance and GEA |  | x
Apply an intersectional lens to Councillor induction program | Not started | Planned for 2024. |  | 2024 | Governance and GEA |  | x
Councillors complete Gender Equitable and Inclusive Leadership training | In progress | Gender Equality training was delivered to all Councillors in April 2021 and refresher training is scheduled for 2023-24. |  | 2023 - 2025 | Governance and GEA |  | x
Regular reporting of Gender Equality data | Ongoing | GE reporting integrated into organisational quarterly reporting mechanisms. |  | 2023 - 2024 | Governance and GEA |  | x
Benchmark other Council programs directed at increasing diversity of representations | Not started | Planned for 2024 |  | 2024 | Governance and GEA |  | x
Investigate pay gaps across the organisation with focus on those levels highlighted in the Workplace Gender Audit report | In progress | Focus on pay differences within the Executive Leadership and Senior Management teams has commenced throughout the annual review period with improvements made. The ongoing focus relates to the banded positions where the pay structure is balanced but the types of roles and classification (FT/PT/Cas) continue to require a gender lens. A project to complete this analysis will be performed in 2024/25 in conjunction with the review of levels across genders. |  | 2023 | People Services & GEA |  |  | x
Investigate pay and level differences across areas of the organisation that are traditionally seen as male or female (reviewing level and responsibility) and develop a plan to address this | In progress | The ongoing focus relates to the banded positions where the pay structure is balanced but the types of roles and classification (FT/PT/Cas) continue to require a gender lens. A project to complete this analysis will be performed in 2024/25 in conjunction with the review of levels across genders. |  | 2023 | People Services & GEA |  |  | x
Review sexual harassment policy through an intersectional lens | In progress | GIA underway and review of sexual harassment policy in progress. |  | 2023 | People Services, Health, Safety & Wellbeing and GEA |  |  |  | x
Workplace Gender Equity and Bystander training | In progress | Nine in-person 'Introduction to Gender Equality' sessions were delivered across Council from Janury to May 2023. Further training booked in late 2023. Online GE training modules to be developed in 2023-24, including a module on bystander intervention. |  | 2022 - 2023 | Culture & Capability and GEA |  |  |  | x
Dismantling Bias Training: Workplace Sexism, Racism, Abelsim and Homophobia | In progress | In-person training for leaders has been scheduled for 2023-24 and an online training module will be developed for staff in 2023-24. |  | 2024 | Culture & Capability and GEA |  |  |  | x
Preventing and Responding to Sexual Harrassment for Leaders training | Complete | Preventing and responding to sexual harassment was included in the Inclusive GE Leadership training program, webinars 2 & 3. Additional in-person training on responding to disclosures has been scheduled for leaders in 2023-24. | Participants reported changes in knowledge, confidence and skills. Leaders were engaged in a review of Council's sexual harassment policy with findings informing the policy review. | 2023 | Culture & Capability and GEA |  |  |  | x
Apply an intersectional gender lens to mandatory Sexual Harrassment training (compliance); conducted face-to-face (preferably) | In progress | An intersectional gender lens was applied to the SH training delivered as part of Inclusive GE Leadership training and the communications delivered to team meetings as part of the 'Introduction to GE' training. Findings from the GIA and SH policy review are being applied to the SH training module review. |  | 2023 | Culture & Capability and GEA |  |  |  | x
Develop process to assess complainants' satisfaction of formal compliants of sexual harassment | Complete | As part of the sexual harassment policy review and related GIA, a process for gaining this information was explored. There are two teams in Council that receive and investigate sexual harassment, a process has been introduced to capture this data and will be reviewed quarterly. The process will formerly be adopted with endorsement of the updated SH policy. | Complainants' satisfaction data has been recorded from 2023 and continues to be recorded for sexual harassment reports. | 2023 | People Services, Health, Safety & Wellbeing and GEA |  |  |  | x
Additional question regarding sexual harassment included in staff survey | Complete | Additional question included in the staff survey. | The staff survey data complements the PMS data, with an ability to provide information e.g. provides deparment/team level information allowing us to identify trends and areas for action. Council acknowledges that not all staff participate in both survey's, and that staff still may choose not to report their experiences of sexual harassment. | 2022 | Learning and Development and GEA |  |  |  | x
Undertake a review of recruitment practices end-to-end using an intersectional gender lens (including employment status) and deliver a recommendations report | In progress | In December 2021, Council developed it's Recruitment and Selection Policy to formalise it's commitment to a fair, transparent and merit-based recruitment process. Equal opportunity and career development principles are included. Planning for the end-to-end recruitment review commenced in late 2022 and the mapping commenced in January 2023. A recruitment consultation was held with the Diversity and Inclusion Group in June 2023. Recommendations report is underway. |  | 2022 | People Services & GEA |  |  |  |  | x
Update policies and processes based on the recommendations of the review | In progress | A review of the following documents was conducted in 2023 and are awaiting finalisation: Code of Conduct, Capability Based Interview Question Guide, Selection Report Template, Selection Notes Template, Reference Check Template, Recruitment and Selection Guidelines, and Induction Checklist |  | 2023 | People Services & GEA |  |  |  |  | x
Train P&C and Hiring Managers on gender equitable and inclusive recruitment practices (refine existing training) | Ongoing | Training for People Services team held in 2022. Training required for hiring managers post the recruitment review. Unconscious bias training for leaders has been scheduled for 2023-24. |  | 2022-2025 | People & Culture |  |  |  |  | x
Unpack merit with the organisation | In progress | Merit was introduced in the Inclusive GE Leadership training program delivered in 2022-23. Further discussions are planned in the scheduled Unconscious Bias and Dismantling Bias training for leaders in 2023-24. Merit is also being considered in the recruitment review and related training for hiring managers. |  | 2023 | Culture & Capability and GEA |  |  |  |  | x
Track and report access to learning and development, secondment and higher duties | Ongoing | In late 2023, work is planned to incorporate this data into the GE dashboard to improve reporting and monitor changes. |  | 2023 | Culture & Capability and GEA |  |  |  |  | x
Promote career development opportunities to part-time and casual staff and track on leaders dashboard | Not started | Planned for in 2024-25 with GE dashboard evolution. Promoting secondments and higher duties opportunities to part-time staff is a measure in Managers work plans under the GE goal. |  | 2023-2025 | Culture & Capability and GEA |  |  |  |  | x
Review secondment opportunities and placements through a gender lens (length/type of role/formal appointment/etc) | In progress | Review commenced March 2023. Initial findings identified that men have higher rates of gaining higher duties (<3 month) which is appointed at the discretion of a line manager and women have higher rates of gaining secondments (>3 month) which undergo a recruitment process. The review confirmed secondments are not replacing permanent appointments. Further investigations are required to understand other factors contributing to the gendered nature of these appointments and what associated benefits are gained through these opportunities. |  | 2023-2025 | People Services & GEA |  |  |  |  | x
Review flexible working policy and Enterprise Agreement through an intersectional gender lens | In progress | Review completed and recommendations provided, including proposed extension to work hours from 6am-6pm to 6am-10pm to provide greater flexibility to staff who require it and a 'right to disconnect' inclusion to ensure staff are empowered to finish work with no expectations to be available after hours or on non-work days. Offer of compressed work week, reduced work hours, changes to start and finish times and retirement transition plans will remain. EBA negotiations in progress awaiting finalisation. |  | 2023 | People & Culture | [5 empty] | x
Update processes for applying for flexible work | In progress | Flexible work policy and processes will be reviewed post EBA approval. |  | 2023 | People Services & GEA | [5 empty] | x
Improved communications regarding flexibility during onboarding | Complete | As apart of Inclusive GE Leadership training, webinar 1, leaders were encouraged to promote flexible work arrangements to all staff. From 2023-24, Managers will have a measure to promote flexible work arrangements to staff under the GE goal in their work plan. Council's onboarding checklist includes a section on flexible work arrangements. A tick box has been added to work plan templates to ensure flexible work arrangements are discussed as part of performance planning and review processes. |  | 2023 | People & Culture | [5 empty] | x
P&C to partner with leaders to understand specific barrier in implementing policy and work to address these | Not started | Pending EBA approval. |  | 2023 - 2024 | Culture & Capability and GEA | [5 empty] | x
Monitor flexibility on Gender Equity dashboard by gender, level and department | In progress | Included in the scope of the gender equality dashboard. |  | 2023 - 2024 | Culture & Capability and GEA | [5 empty] | x
Allocate resourcing to support constrained areas to implement (e.g. additional funds to pilot job-share, cover additional work cover costs, etc) | Void/cancelled | A review of the organisational readiness has highlighted additional work is required before we can commence this action. This action will be postponed to the 2025-29 GEAP. |  | 2023 | [6 empty] | x
Offer flexibility to all existing leaders and assess and remove barriers | Not started | Planned for 2023-24. |  | 2023 - 2024 | Culture & Capability and GEA | [5 empty] | x
Promote flexibility through recruitment for all levels and areas of the organisation | In progress | Council's hybrid work policy is promoted through recruitment as a benefit of working at Council. Staff are required to work on-site 2 days per week. A section in the interview template encourages a conversation about flexible work arrangements. Promoting flexible work arrangements for all staff and increasing men's uptake of paid/unpaid parental leave are included in the measures under the new GE goal in Manager's performance plans. Further promotion of flexible work arrangements will occur with the EBA vote and implementation. |  | 2022 - 2024 | People Services and GEA | [5 empty] | x
Conversation through performance management process to assess flexibility needs for coming year (not constraining it to only at this point) | Complete | Flexibile work arrangements added to My Performance Plans as part of the 23/24 plan process and will remain in the tool ongoing for future review cycles | Prompt to discuss flexible work arrangements formally added into performance planning. | 2023 - 2024 | Learning & Development and GEA | [5 empty] | x
Annual campaign to promote the benefits of flexible working arrangements to the organisation (challenge gender stereotypes when doing so) | Not started | Pending EBA approval. |  | 2023 - 2024 | People Services & GEA | [5 empty] | x
Benchmark parental leave entitlements under the Enterprise Agreement and develop recommendations report for FCC (e.g. remove waiting period, increase secondary carers leave and allow secondary carer to transition to primary carer) | Complete | Benchmarking completed with neighbouring Councils demonstrated Frankston City is on par with parental leave for primary carers, in line or above for parental leave for secondary carers, on par or above for pre-natal leave, above for infectious disease leave, and on par or above for compassionate leave. | The EBA awaiting approval has proposed; doubling secondary carers leave from 15 days to 30 days; included 15 hours of pre-natal leave available for those who are pregnant, undertaking IVF or adopting including the secondary carer; up to 5 days miscarriage leave including the secondary carer; and introduction of 5 days gender affirmation leave. | 2022 - 2023 | People & Culture | [5 empty] | x
Leaders actively promote parental leave to men expecting a new child (both paid and unpaid) | Complete | Managers will be tasked with increasing men's uptake of paid/unpaid parental leave with progress tracked through their performance plans from 2023-24. Through the Inclusive GE leadership training people leaders were informed of the gendered uptake of paid and unpaid parental leave at Council and encouraged to promote paid and unpaid parental leave to expecting father's to progress GE. | Manager's are now accountable for promoting paid and unpaid parental leave to expecting father's. Pending EBA supports expecting father's to attend pre-natal appointments, take miscarriage leave if required and provides up to 30 days parental leave. | 2022 | Managers, Learning & Development and GEA | [5 empty] | x
Review existing return to work program and improve support for parents coming back following parental leave | Not started | Planned for 2023-24. |  | 2023 | Culture & Capability and GEA | [5 empty] | x
Review family violence policy with an intersectional gender lens | Not started | Planned for 2023-24. |  | 2024 | FVAP | [5 empty] | x
Family violence support communicated during onboarding and at induction | In progress | Updated as part of induction checklist review, awaiting finalisation |  | 2023 | Culture & Capability and GEA | [5 empty] | x
Develop Leaders Guide to Responding to Disclosures of Family Violence | Not started | Planned for 2023-24. |  | 2024 | People Services and GEA | [5 empty] | x
Leaders to complete Responding to Disclosures of Family Violence training & refresher training every two years | In progress | Responding to disclosures training scheduled for leaders in 2023-24. |  | 2024 | Culture & Capability and GEA | [5 empty] | x
Annual 16 Days of Activism campaign focused on prevention and support for staff | Ongoing | 2022 16 Days of Activism event held with Phil Cleary as guest speaker. Key note focused on the prevalence of violence against women, the drivers of gendered violence and the actions Council and individuals can take. 2023 campaign will focus on Bystander Intervention, delivery of training and promotion of the 4 D's to bystander action. | 2022 event - 50 people attended the session, with a small number of community members in attendance. Participants were able to identify actions they could take to prevent violence against women. | 2023 - 2025 | GEA | [5 empty] | x
Partner with 2 female and 2 male dominated teams to develop a 3 years project plan with clear targets and measures | Void/cancelled | A review of the organisational readiness has highlighted additional work is required before we can commence this action. Preliminary work to progress this action in the 2025-29 GEAP will commence, a focus on identifying gender-dominated teams, building understanding and buy-in. This action will be postponed to the 2025-29 GEAP. |  | 2023 | [7 empty] | x
Roll out targeted measures with 4 teams including across recruitment, leadership, career development and culture (years 2-4) | Void/cancelled | A review of the organisational readiness has highlighted additional work is required before we can commence this action. This action will be postponed to the 2025-29 GEAP. |  | 2023 - 2024 | [7 empty] | x
Evaluate program with a view to improving and upscaling with additional teams in the next GEAP | Void/cancelled | A review of the organisational readiness has highlighted additional work is required before we can commence this action. This action will be postponed to the 2025-29 GEAP. |  | 2025 | [7 empty] | x
Revise bullying and harrassment policies and protocols through a gender equity and inclusion lens | Not started | Planned for 2023-24. |  | 2023 | People Services and GEA | [6 empty] | x
Team or Department level Gender Equity and Bystander training | In progress | Training commenced through team and department level meetings. The Operations team training is scheduled for September 2023. Bystander Intervention training will be delivered as part of 16 days of activism and an online trainng module will be developed for staff in 2023-24. | From January to May 2023, nine sessions were delivered across Council team meetings. | 2022 - 2023 | Culture & Capability and GEA | [6 empty] | x
Gender Equitable and Inclusive leader training for all leaders with reports | Complete | Three, 2-hour GE webinars were each delivered three times and 14 small group, 90 minute coaching sessions were delivered as part of the Inclusive GE Leadership training program. For people leaders unable to attend online webinars, a recording was made available through Council's online training portal. | People leaders participation in the training reduced as the program progressed; 88% completed webinar 1, 63% completed webinar 2, 57% completed webinar 3 and 40% participated in a coaching session. More than half of seniors leaders have completed 75% of the training program. | 2022 | GEA | [6 empty] | x
Gender Equity and Bystander Training intergrated into induction for new employees | In progress | For new leaders, the recorded webinars from the Inclusive GE Leadership training are available through Council's online training portal. A shortened and interactive version these webinars will be developed into an online training module for leaders in 2023-24. Funding secured to develop online GE training modules for staff in 2023-24. |  | 2023 - 2025 | Culture & Capability and GEA | [6 empty] | x
Develop inclusive language guidelines for employees, contractors and consultants | In progress | Consultation held with Diversity and Inclusion Group in early 2023. Sourcing of existing inclusive language guidelines have been obtained. Currently investigating interactive methods for delivery of these guidelines. |  | 2024 | Culture & Capability and GEA | [6 empty] | x
Training on gendered workplace language and appropriate alternatives | Complete | Although this work was planned for 2025, it was identified during implementation planning that this action required earlier completion. Council recognised changing everyday language reinforce and foster a more equal and respectful workplace and promote inclusivity and a sense of belonging for staff. Inclusive language training has been embedded in GE training delivered to leaders, teams and departments. Inclusive language alternatives were reinforced through inclusive LGBTIQA+ workplace training and also communicated via Council's intranet under the gender equality and pronouns pages. Further education about patriarchy in language and the importance of inclusive language was shared at the 2023 International Women's Day event. A KPI has been included in Managers performance plans from 2023-24. Under the GE goal, Managers need to demonstrate that they are using inclusive language in all communications. | Team and departmental meeting presentations fueled questions related to appropriate alternatives and self-reflections on everyday language. Staff undertaking GIAs have identified recommendations to use inclusive language and this has flowed into strategy documents. | 2025 | GEA | [6 empty] | x
Challenging our Bias training - dismantling sexism, racism, homophobia, ageism and transphobia | In progress | Scheduled for April & June 2024. |  | 2024 | Culture & Capability and GEA | [6 empty] | x
Investigate a whole of organisation reporting approach (e.g. investigate dashboards in Year 1), select approach and create | In progress | An investigation completed and has informed reporting dashboard planning. A GEAP monitoring tool was developed and a Gender Equality dashboard is in development. |  | 2022 | Customer Experience & Transformation, Culture & Capability and GEA
Quarterly dashboard reporting - EMT | Ongoing | Quarterly reporting provided to EMT via department (pulse) and GE report. |  | 2023-2025 | Customer Experience & Transformation, Culture & Capability and GEA
Privacy protocols developed | Complete | Privacy protocols developed | Protocols guiding development of GE dashboard. | 2022 | Governance and GEA
Evaluate existing organisational systems and complete recommendations report on ability to report against all 7 indicators under the Gender Equality Act | Complete | Council reviewed it's capacity to report against all 7 indicators under the GE Act. Actions have been taken to identify how we can capture this data and what data manipulation is required. Governing body data was one indicator Council were unable to meet. Action has been taken to educate Councillors and request data. The review also identified that Council are not collecting intersectional attributes of staff. Whilst this is not a requirement under the Act, it is recommended and Council acknowledges the benefit of applying an intersectional lens to its data. Council is working toward implementation of a new payroll system in 2023-24, that will have capacity to collect and store intersectional data. | The review identified gaps and actions required to enable Council to report against all indicators in future. | 2022-23 | People & Culture
Identify and prioritise key policies (including the Enterprise Agreement) that underpin gender equitable and inclusive workplaces | Ongoing | A review of Council's EBA has been completed with an intersectional gender lens. Pending endorsement of the EBA our flexible work policy will be reviewed. As part of Council's recruitment review a number of key policy documents have been reviewed. As Council continues to progress gender equality it will continue to identify and priorities updates to policies that promote gender equitable and inclusive workplaces. |  | 2022 | People Services & GEA
Deliver Applying an intersectional gender lens to policy training to key People & Culture staff | Complete | P&C team minus payroll attended the two workshop program on the 31/5/22 & 6/6/22 | Participants demonstrated increased understanding of how to apply an intersectional gender lens. Staff who attended the training were able to apply an intersectional gender lens when reviewing recruitment processes. | 2022 | People & Culture
Gender Equity a standing agenda item at EMT and departmental meetings (quarterly) | Ongoing | Quarterly GE report tabled at EMT and Management meetings. |  | 2022-25 | Culture & Capability and GEA
Establish a Gender Equality or Diversity & Inclusion Group with cross-organisational representation and strong leadership support (executive sponsorship) | Complete | Gender Equality Advisory Group formed to support development and implementation of the GEAP. In late 2022, this group evolved into the Diversity and Inclusion Group (DIG) with cross-organisational representation. The gender equality Executive sponsor is also the DIG Executive sponsor. | The DIG met 6 times in 2022-23. The DIG implemented the use of pronouns in the workplace guidelines, associated training and IT mechanisms to share pronouns internally and externally. | 2022 | Learning & Development and GEA
Gender Equality Officer role to deliver on workplace gender programs (1FTE with additional resourcing for GIA's) | Complete | 0.6FTE Gender Equality Advisor appointed September 2023, contracted until June 2024. Planning in progress to make this position permanent. Additional resourcing provided through consultants e.g. Women's Health in the South East (WHISE) and GenderWorks | Since the appointment of a GEA, there has been significant progress with achieving the GEAP and implementation of GIAs within Council. | 2022 | People & Culture
Establish Gender Equity budget line to enable Council to track expenditure for reporting | Complete | A GE budget bid for 2023-24 resulted in a GE budget line being established. | Budget allocated for GE related activities includes development of online training modules, training for leaders, delivery of GE training to our Operations department, 16 days of activism campaign, International Women's Day event and retrospective GIAs. | 2022 | People & Culture and GEA
Develop communications plan to underpin programs and intiatives | Ongoing | Overarching communication strategy developed with communications plans formed per initiative, for example 16 Days of Activism and International Women's Day | Communication plans have resulted in good participation in training, campaigns and events, for example we had 83 people register for the 2023 IWD event. | 2022 | GEA
Celebrate and support International Women's Day annually | Ongoing | Council hosted IWD events in March 2022 and 2023. The 2023 IWD event brought together staff and community, and people of all genders to celebrate women, with a focus on gender inclusive language. This event offered an online attendance option, auslan interpreters and wheelchair accessiblity. | 57 people attended the 2023 event, with 79% of people identifying actions of an ally. These actions included using pronouns, using non-gendered terms, affirming someone's identity, being an active bystander and not making assumptions. | 2022-25 | GEA
P&C and key leaders complete Managing Backlash and Resistance Training (P&C) | In progress | In-person training scheduled for October & November 2023 & March 2024 |  | 2023 | Culture & Capability and GEA
Risk of resistance identified and mitigated in GE activities | Ongoing | Resistance mapping has commenced and continues to be reviewed and updated. Mitigation strategies are idenitified per initiative as part of risk management plans. | Although strategies to reduce backlash and resistance are considered for each GE activity, Council recognises this topic is deeply personal and impacts every one differently, that people have different beliefs and that people respond differently to change. | 2022-25 | GEA
Select one
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X

## 2.2 Resourcing your GEAP
Resourcing your GEAP
Table 2.2 - Allocation of resources to implement the strategies and measures in your GEAP
Recommended
You might consider some or all of the following, in addition to any other aspects you consider relevant: • Who implements the strategies and measures in your GEAP? What role do they perform at what level in your defined entity? • How many staff members/FTE are allocated to implementing the strategies and measures? • Was enough resourcing allocated to successfully implement your strategies and measures? If not, how will this be addressed?
Your Comments
In 2021-22, the Coordinator Learning and Organisational Development and Organisation Development Advisor completed the workplace gender audit, developed the GEAP and commenced implementation of the GEAP and GIAs. Frankston City Council's GEAP was endorsed in March 2022 and the amendments finalised mid-2022. In late 2022, Council recruited a contracted (2-year) part-time (0.6FTE) Gender Equality Advisor to lead the work and establish Council's Diversity and Inclusion Group. This resource combined with additional resourcing through Women's Health in the South East has allowed considerable progress to be achieved in implementing our GEAP and GIAs. Council provided specialised resources to undertake the workforce gender audit and progress report, these resources supported data extraction, relevant de-identifying and coding of data and data analysis to stregnthen the accuracy and outcomes. Council allocated a gender equality budget for 2023-24 to progress achievement of the GEAP and completion of retrospective GIAs. To continue to meet legislative obligations, Council is in the process of securing ongoing allocated resourcing to make the Gender Equality Advisor position permanent.

## 3 Indicators
Workplace Gender Equality Indicators
Table 3 - Workplace gender equality indicators progress
Required | Required | Required | Recommended | [6 empty] | Recommended | Factors key:
|  |  | Factors | [7 empty] | a. b. c. d. e. f. g. | The size of the defined entity, including the defined entity's number of employees. The nature and circumstances of the defined entity, including any barriers to making progress. Requirements that apply to the defined entity under any other Act, including an Act of the Commonwealth. The defined entity's resources. The defined entity's operational priorities and competing operational obligations. The practicability and cost to the defined entity of making progress. Genuine attempts made by the defined entity to make progress.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
Gender composition of all levels of the workforce | Yes | In 2021, women made up majority of Council's workforce and this remains steady in 2023 at 64% (36% men). Of those employed 50% were full time an increase from 47%; 30% were part-time a decrease from 36% and 20% were casual an increase from 17%, revealing more staff were employed FT and casually compared to our baseline audit. Of those employed FT 51% were women an increase from 45%; and 49% were men a decrease from 55%. Of those employed PT 83% were women a slight decrease from 84% and 17% were men a slight increase from 16%. Of those employed casually 71% were women a decrease from 75% and 29% were men an increase from 25%. These findings indicate the gender composition has improved in the full-time category with slight improvement in part-time and casual employment categories. Proportionally, of the women employed at Council, 39% were employed full-time compared to 33%; 39% were employed part-time a decrease from 47% and 22% were employed casually up from 20%. Proportionally, of the men employed 69% were employed full-time a decrease from 72%; 15% were employed part-time a slight drop from 16% and 16% were employed casually, an increase from 12%. In analysing and comparing our 2023 audit findings with our baseline, the overall workforce gender composition remained steady but the findings indicate a progressive shift with the gender composition improving in the full-time category and slight improvement in part-time and casual employment categories. The gap between women and men employed in each category demonstrates progress in the indicator. | [6 empty] | Yes | Council acknolwedges there are gender-dominant industries within our organisation that influence the gender composition of our workforce, resulting in a higher percentage of women. Council also recgonises gendered expectations on women to be primary carers and how this influences their employment and flexibility requirements. However, we have seen a shift in the 2023 audit, with more women transitioning from PT to FT employment, which could be impacted by the current economic climate. Council continues to offer part-time employment opportunities and flexible work arrangements to accomodate caring responsiblities and have also proposed improved leave conditions to support secondary carers within the pending EBA to respond to outdated gendered roles.
Gender composition of governing bodies | No | In 2023, Council provided education to the Mayor and Councillors and invited them to share information about their identity, beyond gender. Three Councillors provided all requested data with remaining governing members prefering not to disclose information about their attributes. Council will be reviewing the induction processes for the new Council term in 2024, and will continue to provide education and opportunities to governing members to provide their personal identity data. | [6 empty] | Yes | Councillors were provided with education and an opportunity to provide their identity data for the first time. Historically, Councilllors have not been asked to disclose personal information and further education is required to support governing body members to share this data publicly. Additionally, Council will continue to deliver community based programs that foster inclusion and belongingness to progress perceptions of safety for governing body members to disclose and for diverse community members to join.
Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender | Yes | The pay gap for median base salary has increased to -4.7% in 2023, from -3.6% in 2021 but for median total remuneration it has reduced to -2.9% in 2023, from -3.1% in 2021. However, when we consider the mean, where the pay gap can be skewed by high salaries of a few individuals, the pay gap has reduced to 0.3% for mean base salary and 0.0% for mean total remuneration in 2023, from 3.7% and 3.4% respectively, in 2021. However, when we consider our workforce proportions 2/3 women and 1/3 men and calculate the weighted average pay gap we reveal a pay gap that benefits men, but when we compare this to our 2021 data set we still see an improvement, a 3.8% reduction in total remuneration indicating and confirming we are making progress. The shift in gender pay gap, utilising the median and mean total remuneration indicates that Council has made progress. The total remuneration includes all aspects of compensation, providing a more comprehensive view of an individual's overall compensation and reflects a more accurate representation of actual earnings. Council recognises that when we factor the proportional women to men (ie the weighted average) we identify significant differences continue to favour men but there have been positive shifts. This shift highlights a favourable change in women's compensation, suggesting that women are narrowing the gap with men. When we conducted an analysis of the weighted average pay gap we saw a 3.8% reduction in total remuneration to 4.5% and a 2.6% reduction in base salary to 4.9%, however when we undertake this form of analysis it reveals the pay gap is benefitting men. This analyse confirms actions taken to progress pay parity has been effective but further efforts are required to continue to progress pay parity. | [6 empty] | Yes | Council proactively focused on pay differences within the Executive Leadership and Senior Management teams with improvements made. The ongoing focus relates to the banded positions where the pay structure is balanced but the types of roles and classification (FT/PT/Cas) continue to require a gender lens. Ongoing analysis will be performed in 2024/25 in conjunction with the review of levels across genders. Council have implemented a gender equality goal with 7 KPIs into manager performance plans. One of the KPIs managers need to respond to is understanding pay disparity within their team and rectifying any gaps.
Sexual harassment in the workplace | Yes | In 2021, Council received no reports of sexual harassment, however our People Matter Survey (PMS) indicated that employees were experiecing sexual harassment, 5% men, 8% women and 15% other. Since 2021, Council have implemented a multi-pronged approach that has increased knowledge and visibility, created safety and promoted the importance of reporting workplace sexual harassment and resulted in 5 reports of sexual harassment. The majority (80%) of complainants were women and 100% of complaints were filed against men. All reports were investigated internally, with 3 dismissals and 1 agreement to stop the behaviour made. Our 2023 People Matter Survey (PMS) results indicated an overall positive change in workplace sexual harassment, with changes in more staff reporting Council takes steps to eliminate bullying, harassment and discrimination and more staff feel safe to challenge inappropriate behaviour at work. Despite this positive indication, the 2023 People Matter Survey (PMS) results showed that 8% of employees, 27 people (333 respondents) experienced sexual harassment in the workplace, no change from 2021 and remains 1ppt above the 2023 local government benchmark (6%). Important to note that in this current period, more staff returned to and spent more time in the workplace so no rise in experiences is a positive signal. However, there was a shift in the gender composition, 4% men, 8% women and 19% self-described gender or prefer not to say reporting experiencing sexual harassment (5% men, 8% women & 15%; 2021). Although there has been an increase in experiences of sexual harassment in 'self-described gender or prefer not to say' workers, overall progress has been seen within this cohort. Most significantly a 28% improvement for this group with more reporting Council takes steps to eliminate bullying, harassment and discrimination and more feel safe to challenge inappropriate behaviour at work but our results still remain well below the local government benchmarks and demonstrate greater efforts are required. But the changes indicate the delivery of LGBTIQA+ inclusion training, the introduction of pronouns, education on gender and sexuality, sexual harassment and gender equality are having an impact. The main types of sexual harassment experienced were suggestive comments (70%) and intrusive questions (65%) with incidences increasing in 2023 compared to 2021. Main perpetrators were colleagues (48%) or immediate manager/supervisor (43%) and majority reported the person was within their work group (56%). When the harassment occurred most either pretended it didn't bother them (48%) or avoided the person/s by staying away from them (48%). The reasons reported for not submitting a formal complaint were 'fear of negative consequences for my reputation' (47%), 'event not serious enough' (37%) or 'won't make a difference' (32%). Overall there has been progress in this indicator with formal reports of sexual harassment received and action taken and overall our PMS results indicate progress. Continued efforts are required to increase staff understanding of how to report sexual harassment, build transparency with Council's response to sexual harassment complaints and foster trust with staff to report. | [6 empty] | Yes | Genuine efforts were made to raise awareness of workplace sexual harassment, increase knowledge and understanding, and encourage reporting. Formal reports of sexual harassment support Council in understanding experiences, identify strategies to prevent and eliminate sexual harassment and monitor trends and risks. Since 2021 audit, Council delivered mandatory online Sexual Harassment training for new and current employees, with every employee expected to complete the course biannually. Similarly, there is a compulsory Workplace Behaviours online module that staff are required to complete too. Within the 'Inclusive Gender Equality Leadership training, sexual harassment education was delivered to leaders across two webinars, inclusive of a review of Council's sexual harassment policy and case studies. As a result of gender equality presentations in team meetings, one team requested a session on sexual harassment to provide greater understanding within their team. Council's CEO included a communication about our zero tolerance of sexual harassment position and details on how to report within their weekly CEO email. A sexual harassment page was created on Council's intranet and this was promoted through education sessions and the CEO email. Council have implemented a gender equality goal into manager performance plans. One of the KPIs includes promoting the reporting of bullying, harassment and discrimination and sexual harassment to staff. In 2023, Council commenced a formal review of our Sexual Harassment policy that included a gender impact assessment. The policy review will be completed in 2023-24 and will include a review of the online training module. Council has also booked training for leaders in 2024 on responding to disclosures of sexual harassment and family violence. Greater work by Council is required to eliminate sexual harassment within the workplace and to reduce the barriers in reporting for staff. Council has included sexual harassment reporting in quarterly gender equality reports to increase visibility for Managers and will continue to identify pathways to increase transparency of sexual harassment reporting within the workplace.
Recruitment and promotion practices in the workplace | Yes | Recruitment: In 2023, 226 people were recruited; 66% women, 33% men and 1% self-described gender, representing small progress of a 2ppt increase for women and a 1ppt increase in self-described gender since 2021 and continues to reflect the workforce gender composition. Of those recruited, 23 people were recruited into a manager or supervisor level and within this group 57% were women and 43% were men, not reflective of the gender composition of the workforce (58% women and 42% men; 2021). Disproportionately, men were recruited to leadership positions in two consecutive reporting periods. PMS results maintained above the LG benchmark, 65% of respondents believe the recruitment processes at Council are fair. Retention: In the reporting period, 163 people left Council 56% women, 44% men and 1% self-described gender, compared with 64% women and 36% men in 2021. The findings show less women are leaving but more men are leaving Council. If the current pattern continues, where more women than men are joining Council and more men than women leave the disparity of the men:women workforce ratio will further. Career Development & Training Opportunities: In 2023, more women were provided with opportunities for career developments and training, 71% women and 29% men, not reflective of the gender workforce ratio. PMS results demonstrated this was the only indicator that had achieved progress, most (64%) respondents were satisfied with the way their learning and development needs had been addressed, up 7ppt. Promotion: Of the 14 people who were promoted at Council, 64% were women and 36% were men, mirroring the current workforce gender composition and showing no change since 2021. Promotions overwhelmingly, were awarded to those working full-time, 93%. PMS results maintained LG benchmark, with 47% of respondents believing the promotion processes at Council are fair; 53% of respondents feeling they have an equal chance at promotion; and 57% reporting satisfication with the opportunities to progress at Council. The PMS survey results overall show no progress on this indicator however when we consider actions taken on higher duty and secondment appointments we see progress. Higher Duties: Progress has been seen in the appointments of those performing higher duties in 2023 (170) 63% women and 37% men, reflecting the workforce gender composition, an improvement on 2021 (150) where higher duties were awarded 52% women and 48% men. Further to this progress, the appointment of higher duties to full-time workers decreased from 88% to 82% (6ppt), a 6% improvement in higher duties being awarded to non-full time staff. Secondments: Council offered more secondments, with 99 opportunities provided to staff compared with only 16 secondments in the 2021 audit. Of the 16 secondments in 2021, 6% were awarded to men and 94% were awarded to women. In 2023, we saw a significant improvement with 41% men and 59% women awarded secondments, a gender split more reflective of Council's workforce composition. Council made progress in appointing higher duties and secondments more equally across genders, providing more secondment opportunities to staff and progressing the distribution of higher duty opportunities to non-full time employees. | [7 empty] | Council proactively informed leaders of the disparity that was highlighted in the 2021 audit, with more men awarded higher duties and more women awarded secondments. Leaders were tasked with reviewing their appointments of higher duties and secondments with a gender lens. In December 2021, Council developed it's Recruitment and Selection Policy to formalise it's commitment to a fair, transparent and merit based recruitment process and equal opportunity and career development principles are included. A recruitment consultation was held with Council's Diversity and Inclusion Group and further analysis of Council's recruitment practices are underway. In reviewing Council's EBA, there has been a proposal to double parental leave for secondary carers, increasing from 15 to 30 days and provision of 15 hours of pre-natal leave available for secondary carers for pregnancy, In Vitro Fertilization (IVF) or adopting and up to 5 days miscarriage leave for secondary carers. This change will better support men planning or having children. The incoming EBA has also added clarity for those employees transitioning to retirement, thereby better supporting workers who are planning for retirement. With the adoption of the EBA greater promotion of staff flexibility and leave will be promoted across the organisation and we expect to see greater utilisation in our 2025 audit. Council have implemented a gender equality goal with 7 KPIs into manager performance plans. One of KPIs includes creating opportunities for part-time workers to access higher duties and secondments.
Availability and utilisation of terms, conditions and practices relating to: - family violence leave; and - flexible working arrangements; and - working arrangements supporting employees with family or caring responsibilities | No | Flexible Working Arrangements (FWA): In 2023, less people had formal FWA, down 9ppt (11% decrease), 79 compared to 88, 69% women and 31% men, similar to 2021 and reflective of the current workforce gender split. Proportionally, 6% of the total population of men and 7% of the total population of women had a FWA, demonstrating more equal uptake of FWA. PMS results showed 79% of respondents feel supported by their manager to work flexibly and 76% are confident that if they requested FWA it would be given due consideration. Council continue to support and promote informal FWA to better accommodate for situational flexibility required by staff. To better understand if all staff are having conversations about FWA, a prompt has been added to the work performance plan tool for 2023-24. Parental Leave (PL): The gender composition of those who took parental leave in 2023, 70% women and 30% men, remains in line with 2021 data (71% women and 29% men) and is not reflective of the current workforce gender composition. However, there was a positive shift in the average number of weeks of parental leave taken, women decreased from 111.5 weeks to 22.7 weeks and men increased from 5.3 to 6.4 weeks. Proportionally, women are represented 2.5 times more than men, ie. 4% of the total population of men and 10% of the total population of women used parental leave in 2023. The length of parental leave taken by men shows some progress, however women continue to be disproportionately impacted by this time out of the workforce. Carers Leave (CL): In 2023, there were similar rates of carer's leave use, 98 compared with 92 in 2021, of those taking carer's leave 20% were men, 79% were women and 1% self-described gender. The gender split of those taking carer's leave in 2021 and 2023 are not reflective of the current workforce gender composition. Of the 98 people who took carers leave in 2023, 59 (63%) were part-time and of those who were part-time 54 (57%) were women. Carer's leave uptake continues to be skewed toward part-time women. Family Violence (FV): In 2023, 7 employees utilised Family Violence leave, 86% (6) were women. Demonstrating slight progress from 2021 where 5 people used FV leave, 80% (4) were women. The PMS results remained steady with 86% of respondents reporting Council would support them if they needed to take family violence leave, 1ppt below the LG benchmark. Overall, no progress has been made in this indicator but there are small signals of progress for example, most staff feel supported to work flexibly, men are using more parental leave and more staff have taken family violence leave. | [6 empty] | Yes | Council offers and promotes flexibile work arrangements but is aware that leaders and their staff have informal arrangements that are not captured through our system. This approach has been welcomed by staff and managers to improve ease and more responsive to accomodate situational needs. For example, starting later or finishing earlier and/or working from home and/or switch work days or work hours to better manage care responsibilities. Council recognises the importance of flexibile work arrangements and in the pending EBA have extended work hours, from 6am-6pm to 6am-10pm and a 'right to disconnect' clause. Council recognise we need to be able to monitor that all areas of the business and workers are having discussions about FWA and as such implemented a check box within online performance plans to prompt discussions throughout the year and allow us to monitor. In 2022-23, through Inclusive Gender Equality Leadership training Council actively encouraged leaders to promote parental leave to expecting fathers as an easy action all leaders could take to progress gender equality. Council have implemented a gender equality goal with 7 KPIs into manager performance plans. The KPIs include: completing gender equality training; understanding pay disparity within their team and rectifying; creating opportunities for part-time worker to access higher duties and secondments; promote staff benefits and supports to staff including flexible work arrangements, paid and unpaid leave to men and family violence leave; promote the reporting of bullying, harassment and discrimination and sexual harassment; use inclusive lanugage in all communications; ensure gender impact assessments are completed for all relevant initiatives. Council has applied an intersectional gender lens to their upcoming EBA and this has resulted in a doubling in a secondary carer's paid parental leave from 3 to 6 weeks and three new clauses: miscarriage leave (for employees or their spouse/partner), pre-natal leave (15 days paid) and gender affirmation leave (5 days paid). The incoming EBA has introduced clauses supporting hybrid work arrangements, extension to the spread of working hours from 6am-6pm to 6am-10pm, an ability for staff to work a compressed work week and an employee's right to disconnect. These additions are all centred on progressing Council as a flexible and fair employer of choice. Council anticipates the impact of these actions will be evident in the 2025 audit and progess report.
Gendered segregation within the workplace | Yes | In 2023, occupational segregation data showed women were overrepresented in 57% (4) of categories as Managers; Professionals; Community and Personal Service Workers; and Clerical and Administrative Workers whereas men were overrepresented 43% (3) of the categories as Technicians and Trades Workers; Machinery Operators and Drivers; and Labourers. Since 2021, there has been progress in the Manager category, shifting the greatest representation from men (57%) to women (69%), better reflecting the workforce gender composition. Greater gender segregation has been revealed in 4 categories, in 2023. Men represent more of the workforce composition in the technician and trade workers category, 87% up from 73% and labourers category 64% up from 61%. A new category has presented in 2023, machinery where 100% of the workforce are men. Women represent more of the workforce composition in clearical and administrative workers category 71% up from 68% and community and personal service workers 89% up from 88%. Professionals maintained steady, with women representing the majority, 74% compared to 26% men. Overall there has been slight progress in this indicator, in our Manager workforce composition which now better reflects our workforce composition and whilst PMS results suggest no overall progress, improvements in areas relating to cultural safety are visible. From the PMS survey, gendered segregation covered respect, inclusion and safety topics with respondents either agreeing or disagreeing with specific questions. In 2023, 82% of respondents agreed that Council uses inclusive/respectful images/language, up 5 percentage points from 2021 (77% agreed) but remains 2 percentage points below the local government (LG) benchmark of 84%. The gender split agreeing with usage of inclusive/respectful images/language was Men 86%, Women 81%, Non-Binary 69% which has improved from 2021 when it was Men 80%, Women 80%, Non-Binary 46%. In 2023, 83% of respondents felt culturally safe at work a positive increase of 4 percentage points (ppt) from 2021 (79%) and up 1 percentage point from LG benchmark. Although we saw a positive change for men 85% (up from 79% in 2021) and women 85% (up from 83% in 2021) there was a decrease in non-binary folks 44% (down from 46% in 2021). The PMS 2023 results found the majority of respondents agreed their manager treated them with dignity/respect (83%, -1 ppt from LG), agreed they could be themselves at work (80%, -1 ppt from LG), agreed that work was allocated fairly regardless of gender (79%, -2 ppt from LG) and felt as if they belonged (74%, +2 ppt from LG). However, 68% of respondents reported witnessing one or more barriers to success (-5ppt from LG) and experienced one or more barriers to success (-4ppt from LG). Bullying: In 2023, 17% of PMS respondents reported experiencing bullying, an improvement of 6 percentage points from 2021, but continues to be 3 percentage points above the LG benchmark. There is a marked experiential difference across genders of those who reported experiences of bullying 8% of men, 16% of women and 69% of Non-Binary respondents. Compared to 2021, men and women have seen decreases in bullying incident, (-10ppt for men and -4ppt women) but there has been a worsening for non-binary folk up 15 percentage points (54%). The main forms of bullying were incivility (75%, up 8ppt from 2021) and exclusion or isolation (55%, up 1ppt from 2021) and repondents reported that majority of bullying was perpetrated by an immediate manager/supervisor, 73% of the time. For perspective, current gender split of managers/supervisors is 43% men, 57% women. Of the respondents who were women, 68% reported the bullying was perpetrated by an immediate manager/supervisor and of respondents who were non-binary 55% reported the bullying was perpetrated by a colleague. Compared to 2021, the PMS results have shown a positive change in the number of respondents not telling anyone about experiencing bullying, dropping from 14% to 11% in 2023 and of those 5% were women and 18% were non-binary. Fear of negative consequences and thinking it won't make a difference were the main drivers for respondents not submitting a formal complaint, recording worsening results in 2023 (average 45%) compared to 2021 (average 21%). The PMS results have also highlighted that more respondents in 2023 do not know how to make a complaint and/or are being advised not to make a complaint (10% in 2023 cf 2% in 2021). Discrimination: In 2023, 8% of respondents experienced discrimination, up 2 percentage points from 2021 (2ppts above the LG benchmark) and rates have increased across all genders. In 2023 6% men (up from 4% in 2021), 7% women (up from 6% in 2021) and 44% non-binary had experienced discrimination, a significant increase from the 12% in 2021. PMS respondents reported denied opportunities for promotion, training/PD or secondment as the main forms of discrimination experienced. 89% of respondents cited that their immediate Managers/supervisors were behaving in a discriminatory manner and of concern is that over a 1/4 of respondents did not tell anyone. | [6 empty] | Yes | Council recognises the importance of working with gender-dominant areas of Council to understand enablers and barriers to inform strategies and solutions but acknowledges organisational readiness needs to evolve to enable this action to be successful. Council have proposed postponing actions related to working with gender-dominant sectors to ensure a preliminary work is completed to enable success. Progress has been focused on creating changes where possible through recruitment pathways whilst simultaneously building a foundation of knowledge to support change readiness and creating psychological safety for staff and prospective staff who join Council and move into single gender-dominant departments. Council will continue to improve these efforts and lay the ground work required to achieve related GEAP actions in 2025-29. Council recognises the increase in experiences of sexual harassment, harassment and bullying by staff who self-describe their gender could be linked with greater workplace interactions post covid lockdowns, greater education about sexual harassment and/or increased visibility of gender equality related work. In 2022-23, Council delivered education on gender and sexuality, gender equality, the importance of inclusive communications and offered all staff LGBTIQA+ inclusion training with the implementation of 'usage of pronouns in the workplace' guidelines. Greater visibility and focus on gender diversity could be presenting resistance and backlash by some staff with differing view points resulting in experiences of bullying and harassment of staff who self-describe their gender. Council has scheduled Bystander Intervention for staff as part of our 16 days of activism campaign in 2023 and will continue to promote the importance of reporting complaints of bullying. Council has scheduled a review of our Bullying and Harassment policy for 2023-24 and will continue to promote complaint processes to staff and increase transparency of investigation outcomes. Council has promoted Stopline our anonymous reporting option within the context of sexual harassment reporting but further education is required to workers of this option for other forms of bullying and discrimination.
Example(s)
Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  | a | b | c | d | e | f | g
Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## Examples (hidden)
1 Gender impact assessments
| Title | Subject | Description | Status |  |  | Confirm if actions taken |  |  |  | Describe actions taken |  | Confirm intersectionality considered |  | Explain intersectional lens applied
| What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. |  |  | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. |  |  |  | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. |  | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. |  | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
| Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review |  |  | Yes |  |  |  | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. |  | Yes |  | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
2.1 Strategies and measures
| Strategies and measures | Status | Status description | Evaluation of success | [6 empty] | Timeline | Responsible | Relevant indicator(s)
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | [6 empty] | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator.
| Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | [6 empty] | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X
3 Workplace Gender Equality Indicators
| Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  |  | a | b | c | d | e | f | g
| This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
| Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
| Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## (Hidden) REF (hidden)
Policy | New | Yes | Select one | Yes
Program | For Review | No | Complete | No action taken
Service |  |  | In progress
Ongoing
Not started
Void/cancelled